## Flights
equipmentName | flightNumber | airCraftModel | currentStation | bayNumber | taskStartTime | departure
Flight0 | 101 | Airbus A320-100/200 | MAA | 3 | 9:00 | 9:45 | 0 | 45
Flight1 | 121 | Airbus A320-600 | MAA | 5 | 10:18 | 11:00 | 78 | 120
Flight2 | 343 | Airbus A340-600 | MAA | 4 | 10:33 | 11:15 | 93 | 135
Flight3 | 360 | Airbus A320-100/200 | MAA | 2 | 11:30 | 11:50 | 150 | 170
Flight4 | 144 | Airbus A340-600 | MAA | 4 | 12:00 | 13:00 | 180 | 240
Flight5 | 511 | Airbus A320-100/200 | MAA | 8 | 14:45 | 15:15 | 345 | 375

## Tasks
flightNumber | taskDetail | duration | startTime | endTime | statusOfTask | actualStartTime | actualEndTime | timeDifference | department | staffName | start Time(D-) | actual Start Time(D-)
121 | CARGO LOADING | 20 | 10:18 | 10:38 | Yet To Start | 10:18 | 10:38 | 20 | Ramp | RAMST1 | 42 | 42
121 | FUELLING | 20 | 10:22 | 10:42 | Yet To Start | 10:22 | 10:42 | 20 | Ramp | RAMST1 | 38 | 38
121 | CABIN APPEARANCE | 8 | 10:29 | 10:37 | Yet To Start | 10:29 | 10:37 | 8 | Ramp | RAMST1 | 31 | 31
121 | BRIDGE CLEARED | 5 | 10:32 | 10:37 | Yet To Start | 10:32 | 10:37 | 5 | Ramp | RAMST1 | 28 | 28
121 | BAGGAE LOADING | 17 | 10:38 | 10:55 | Yet To Start | 10:38 | 10:55 | 17 | Ramp | RAMST1 | 22 | 22
121 | LOADSHEET ONBOARDING | 5 | 10:50 | 10:55 | Yet To Start | 10:50 | 10:55 | 5 | Ramp | RAMST1 | 10 | 10
121 | PUSH BACK REPORTING | 5 | 10:50 | 10:55 | Yet To Start | 10:50 | 10:55 | 5 | Ramp | RAMST1 | 10 | 10
121 | HOLDS CLOSED | 5 | 10:55 | 11:00 | Yet To Start | 10:55 | 11:00 | 5 | Ramp | RAMST1 | 5 | 5
343 | GATE CKIN | 20 | 10:35 | 10:55 | Yet To Start | 10:35 | 10:55 | 20 | Gate | GATST1 | 40 | 40
343 | CABIN CREW REPORTING | 5 | 10:40 | 10:45 | Yet To Start | 10:40 | 10:45 | 5 | Gate | GATST1 | 35 | 35
343 | PILOT REPORTING | 5 | 10:50 | 10:55 | Yet To Start | 10:50 | 10:55 | 5 | Gate | GATST1 | 25 | 25
343 | 1st COACH REPORTING | 10 | 10:52 | 11:02 | Yet To Start | 10:52 | 11:02 | 10 | Gate | GATST1 | 23 | 23
343 | GATE NOSHOW REPORTING | 5 | 11:05 | 11:10 | Yet To Start | 11:05 | 11:10 | 5 | Gate | GATST1 | 10 | 10
343 | LAST PAX ONBOARDING | 5 | 11:05 | 11:10 | Yet To Start | 11:05 | 11:10 | 5 | Gate | GATST1 | 10 | 10
343 | CARGO LOADING | 20 | 10:33 | 10:53 | Yet To Start | 10:33 | 10:53 | 20 | Ramp | RAMST2 | 42 | 42
343 | FUELLING | 20 | 10:37 | 10:57 | Yet To Start | 10:37 | 10:57 | 20 | Ramp | RAMST2 | 38 | 38
343 | CABIN APPEARANCE | 8 | 10:44 | 10:52 | Yet To Start | 10:44 | 10:52 | 8 | Ramp | RAMST2 | 31 | 31
343 | BRIDGE CLEARED | 5 | 10:47 | 10:53 | Yet To Start | 10:48 | 10:53 | 5 | Ramp | RAMST2 | 28 | 28
343 | BAGGAE LOADING | 17 | 10:53 | 11:10 | Yet To Start | 10:53 | 11:10 | 17 | Ramp | RAMST2 | 22 | 22
343 | LOADSHEET ONBOARDING | 5 | 11:05 | 11:10 | Yet To Start | 11:05 | 11:10 | 5 | Ramp | RAMST2 | 10 | 10
343 | PUSH BACK REPORTING | 2 | 11:05 | 11:10 | Yet To Start | 11:05 | 11:10 | 2 | Ramp | RAMST2 | 10 | 10
343 | HOLDS CLOSED | 5 | 11:10 | 11:25 | Yet To Start | 11:10 | 11:25 | 5 | Ramp | RAMST2 | 5 | 5

## Employees
Email | secretPassword | userName | userType | UserDepartment
RAMST1 | Pa55word | RAMST1 | Staff | Ramp
RAMST2 | Pa55word | RAMST2 | Staff | Ramp
GATST1 | Pa55word | GATST1 | Staff | Gate
RAMSU1 | Pa55word | RampSup | Super Visor | Ramp
GATSU1 | Pa55word | GateSup | Super Visor | Gate
AIRMG1 | Pa55word | AIRMG1 | Manager | Manager
TKTSup | Pa55word | TKTSup | Super Visor | ATO
CKNSup | Pa55word | CKNSup | Super Visor | Check in
BagSup | Pa55word | BagSup | Super Visor | Bags
SecSup | Pa55word | SecSup | Super Visor | Security
OPSSup | Pa55word | OPSSup | Super Visor | Operations
AME | Pa55word | AME | Super Visor | Engineering

## Departments
flightNumber | departmentName | superVisorName | sheduledStartTime | sheduledEndTime | sheduledDuration | actualStartTime | actualEndTime | statusOfDepartment
121 | ATO | TKTSup | 10:18 | 10:38 | 28 | 10:18 | 10:38 | Yet To Start
121 | Check in | CKNSup | 10:18 | 10:38 | 25 | 10:18 | 10:38 | Yet To Start
121 | Bags | BagSup | 10:18 | 10:38 | 26 | 10:18 | 10:38 | Yet To Start
121 | Security | SecSup | 10:18 | 10:38 | 24 | 10:18 | 10:38 | Yet To Start
121 | Gate | GateSup | 10:18 | 10:38 | 35 | 10:18 | 10:38 | Yet To Start
121 | Ramp | RampSup | 10:18 | 10:38 | 37 | 10:18 | 10:38 | Yet To Start
121 | Operations | OPSSup | 10:18 | 10:38 | 16 | 10:18 | 10:38 | Yet To Start
121 | Engineering | AME | 10:18 | 10:38 | 21 | 10:18 | 10:38 | Yet To Start
343 | ATO | TKTSup | 10:18 | 10:38 | 28 | 10:18 | 10:38 | Yet To Start
343 | Check in | CKNSup | 10:18 | 10:38 | 25 | 10:18 | 10:38 | Yet To Start
343 | Bags | BagSup | 10:18 | 10:38 | 26 | 10:18 | 10:38 | Yet To Start
343 | Security | SecSup | 10:18 | 10:38 | 24 | 10:18 | 10:38 | Yet To Start
343 | Gate | GateSup | 10:18 | 10:38 | 35 | 10:18 | 10:38 | Yet To Start
343 | Ramp | RampSup | 10:18 | 10:38 | 37 | 10:18 | 10:38 | Yet To Start
343 | Operations | OPSSup | 10:18 | 10:38 | 16 | 10:18 | 10:38 | Yet To Start
343 | Engineering | AME | 10:18 | 10:38 | 21 | 10:18 | 10:38 | Yet To Start